## Sheet1
Date	To Do:
04/12/2018	Start a draft and search for helpful tools and articles
11/12/2018	Experiment with different software to find the optimal one, and meet the client
22/01/2019	Finish the Technical Design Document and the system overview, and make a early prototype
29/01/2019	Finsh the Class Diagram and the entire system design and add in moveable hands that can pick up objects
05/02/2019	Finally Complete the Class Diagrams and make more environments
12/02/2019	Add NPCs with workable AI with a completeable scenerio
19/02/2019	Add in additional animations with a workable AI
26/02/2019	Make a complete Scenerio, make a Presentation for the Milestone Review, and an Evalution

## Sheet2
Date	To Do:
05/03/2019	Make Crossing the Road & Restaurant Scenerio
12/03/2019	Make Working in an Office Scenerio
19/03/2019	Make Clothes Shopping Scenerio
26/03/2019	Make Coffee Shop Scenerio
02/04/2019	Touch up all the Scenerios
09/04/2019	Add the Analytics
16/04/2019	Meet with the clients for a demo and take notes, start Project Report
23/04/2019	Implement fixes suggested by client and meet with client with a completed version, continue Project Report
30/04/2019	Continue Project Report and do an Start Evaluation
07/05/2019	Finish Project Report & Evaluation then Hand-in Work
14/05/2019	Make Viva Presentation then present it