## Sheet1
Date | To Do:
2018-12-04 | Start a draft and search for helpful tools and articles
2018-12-11 | Experiment with different software to find the optimal one, and meet the client
2019-01-22 | Finish the Technical Design Document and the system overview, and make a early prototype
2019-01-29 | Finsh the Class Diagram and the entire system design and add in moveable hands that can pick up objects
2019-02-05 | Finally Complete the Class Diagrams and make more environments
2019-02-12 | Add NPCs with workable AI with a completeable scenerio
2019-02-19 | Add in additional animations with a workable AI
2019-02-26 | Make a complete Scenerio, make a Presentation for the Milestone Review, and an Evalution

## Sheet2
Date | To Do:
2019-03-05 | Make Restaurant Scenerio
2019-03-12 | Make Working in an Office Scenerio
2019-03-19 | Make Clothes Shopping Scenerio
2019-03-26 | Make Coffee Shop Scenerio
2019-04-02 | Touch up all the Scenerios
2019-04-09 | Add the Analytics
2019-04-16 | Meet with the clients for a demo and take notes, start Project Report
2019-04-23 | Implement fixes suggested by client and meet with client with a completed version, continue Project Report
2019-04-30 | Continue Project Report and do an Start Evaluation
2019-05-07 | Finish Project Report & Evaluation then Hand-in Work
2019-05-14 | Make Viva Presentation then present it